## Project Tracker
Project Tracker
S. No. | Name | Project | Start | End | Task | Time | Status | Notes
1 | Avinash | swasstationary.in |  |  | Product Details Page | 4 Hrs | In Progresss | Design Issue
[5 empty] | Home Page Large Image Link by Brands | 2 Hrs | Pending | Provided by Client thorugh Mail (Today)
|  | Skill CMS Job Prtal |  |  | Home New Page Design |  | Pending | Bindu sir Working
[5 empty] | Employer Registration Form (In Employer Panel) |  | Pending | Review and Implement (Reference site)
|  | Richeera |  |  | Product details Page | 4 Hrs | In Progrss | Find Html By Gaya Sir (Today)
[5 empty] | Create Member New functionality | 2 Hrs | Pending
|  | sepremebooks.com |  |  | Create Library for upload pdf/image |  | Pending | Need To discuss with subodh sir
2 | Subodh | Skill CMS Website |  |  |  |  | In Progress | Backend Complete
|  | Employee Panel |  |  |  |  | Almost Complete | Few Changes in progress discussed in last meeting for Numeric badges and Employee Bulk Upload